## Sheet1
Phase	Task	Oct				Nov				Dec				Jan				Feb				Mar				Apr
		W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4
Research	Rules of Poker														Exam Period
	Frameworks
	Feasibility
	Server Hosting
	Randomness
	Market
	Planning
⚑ Research Complete
Planning	Documents														Exam Period
	Vision and Scope
	Specification
	Wireframes
	Code-style Guide
	Pseudocode
	Texas Hold’em
	Server
⚑ Planning Complete
Development	Prototype Backend														Exam Period
	Texas Hold’em
	Implement CI
	Integrate Basics to Android
	Develop Backend Further
	Implement Databases
	Implement Helper Classes
	Development Freeze
	Test Texas Hold’em fully
	Test databases validation
	Ensure backend can work alone
	Develop Frontend
	Implement Activities
	Link activities to Backend
	Develop Server
	Basic Connectivity
	Passing Game Data
	Disconnection Tolerance
⚑ Development Complete
Review	User Review + Feedback														Exam Period
	Code Review
	Quality Review
	Resources
	UI Intuitiveness
	Look and Feel
Polishing Up	Final Testing
	Black Box Testing
	White Box Testing

Parallel	Interim Report
	Dissertation

																															Z|